## Eku Flowline Integrity Status
flowline | location | design_life_span | year_Installed_or_replaced | years_installed_or_laid | planned_replacement_period | latest_replacement_date | complete_system_failure_indicator | preventive_maintenace_plan | remarks
Awoba Northwest Well 1L | Ekulama 1 | 15 | 2002 | 18 | Replace by 2015 | 2017 | Flowline as Expired | 1. Complete replacement by 2018 | 1KM flow line Sectional replacement in 2017. Clampping @RoW at 2-points.
Awoba Northwest Well 1S | Ekulama 1 | 15 | 2002 | 18 | Replace by 2015 | 2017 | Flowline as Expired | 1. Complete replacement by 2018 | Clampping @RoW at 2-points.
Awoba Northwest Well 2L | Ekulama 1 | 15 | 2019 | 2 | Replace by 2031 | 2033 |  | Check and Service Cathodic Protection System - OK | Newly Installed
Awoba Northwest Well 2S | Ekulama 1 | 15 | 2019 | 2 | Replace by 2031 | 2033 |  | Check and Service Cathodic Protection System - OK | Newly Installed
Well 3L | Ekulama 1 | 15 | 2017 | 4 | Replace by 2030 | 2017 |  | Check and Service Cathodic Protection System - OK | This flowline was replaced in 2017.
Well 40T | Ekulama 1 | 15 | 2009 | 11 | Replace by 2016/ 2022 | 2024/ 2016 | Flowline at Risk | 1. Fix all Cathodic Protection issues. 2. Repair field joint wrapping. 3. Carry out 3 yearly UT (in plot/on plot piping) inspection of our flow lines and manifold piping's. 4. Increase ROW Surveillance. | No clamp
Well 5L | Ekulama 1 | 15 | 2015 | 10 | Replace 2022 | 2025 | Flowline at Risk | 1. Fix all Cathodic Protection issues. 2. Repair field joint wrapping. 3. Carry out 3 yearly UT (in plot/on plot piping) inspection of our flow lines and manifold piping's. 4. Increase ROW Surveillance. | Sectional replacement @ ROW in 2017 with 2 clamps
Well 5S | Ekulama 1 | 15 | 2015 | 10 | Replace 2022 | 2025 | Flowline at Risk | 1. Fix all Cathodic Protection issues. 2. Repair field joint wrapping. 3. Carry out 3 yearly UT (in plot/on plot piping) inspection of our flow lines and manifold piping's. 4. Increase ROW Surveillance. | 3 nos of Clampping done
Well 17S | Ekulama 1 | 15 | 1994 | 26 | Replace by 2018 | 2009 | Flowline Expired | 1. Fix all Cathodic Protection issues. 2. Complete Replacement by 2018 3. Increase ROW Surveillance. | No clamps
Well 27L | Ekulama 1 | 15 | 2019 | 2 | Replace by 2032 | 2034 |  |  | Replaced in 2019. Not in functional.
Well 27S | Ekulama 1 | 15 | 1994 | 26 | Replace by 2018 | 2009 | Flowline Expired | 1. Fix all Cathodic Protection issues. 2. Complete Replacement by 2018 3. Increase ROW Surveillance. | Clamping at F/L Riser. 1-Clamp on RoW
Well 35L | Ekulama 1 | 15 | 2018 | 4 | Replace by 2030 | 2032 |  |  | No clamp
Well 35S | Ekulama 1 | 15 | 2015 | 10 | Replace by 2022 | 2025 |  | 1. Fix all Cathodic Protection issues. 2. Repair field joint wrapping. 3. Carry out 3 yearly UT (in plot/on plot piping) inspection of our flow lines and manifold piping's. 4. Increase ROW Surveillance. | No clamp
Well 30T | Ekulama 1 | 15 | 1994 | 26 | Replace by 2018 | 2023 | Flowline Expired | Full Replacement needed | Flowline leaking on the WHD riser. Flowline has exceeded its design life span.Requires urgent replacement.
Well 18T | Ekulama 2 | 15 | 2017 | 4 | Replace by 2030 | 2032 |  | Check and Service Cathodic Protection System - OK | No clamp
Well 36L | Ekulama 2 | 15 | 2016 | 11 | Replace by 2031 | 2016 | Flowline at Risk | 1. Fix all Cathodic Protection issues. 2. Repair field joint wrapping. 3. Carry out 3 yearly UT (in plot/on plot piping) inspection of our flow lines and manifold piping's. 4. Increase ROW Surveillance. | No clamp
Well 36S | Ekulama 2 | 15 | 2016 | 10 | Replace by 2031 | 2016 | Flowline at Risk | 1. Fix all Cathodic Protection issues. 2. Repair field joint wrapping. 3. Carry out 3 yearly UT (in plot/on plot piping) inspection of our flow lines and manifold piping's. 4. Increase ROW Surveillance. | No clamp
Well 26L | Ekulama 2 | 15 | 2010 | 10 | Replace by 2023 | 2025 |  |  | No Clamp
Well 34L | Ekulama 2 | 15 | 2017 | 4 | Replace by 2030 | 2032 |  | Check and Service Cathodic Protection System - OK | No clamp
Well 3S | Ekulama 2 | 15 | 2013 | 4 |  |  |  |  | Not applicable
W/38S | Ekulama 2 | 15 | 2013 | 8 |  |  | Flowline at Risk |  | Multiple clamps on Flow line and well is curently closed on flow line leak. Requires complete replacement considering the numerous clamps.
Well 38L | Ekulama 2 | 15 | 2013 | 8 | Replace by 2022 | 2027 |  | 1. Fix all Cathodic Protection issues. 2. Repair field joint wrapping. 3. Carry out 3 yearly UT (in plot/on plot piping) inspection of our flow lines and manifold piping's. 4. Increase ROW Surveillance. | Though not expired,we have challenges already with them.Sectional replacement in 2017. 7 nos of Clampping done.Flow line require full replacement considering the numbers of clamps.
Well 38S | Ekulama 2 | 15 | 2013 | 8 | Replace by 2022 | 2027 |  | 1. Fix all Cathodic Protection issues. 2. Repair field joint wrapping. 3. Carry out 3 yearly UT (in plot/on plot piping) inspection of our flow lines and manifold piping's. 4. Increase ROW Surveillance. | 3 nos of Clampping done
Well 21L | Ekulama 2 | 15 | 2017 | 3 | 2032 | 2032 |  | 1. Ensure adequate Cathodic Protection is in place. 2. Carry out 3 yearly UT (in plot/on plot piping) inspection of our flow lines and manifold piping's. 3. Increase ROW Surveillance. | Flowline constructed in 2017,One Clamp@ ROW done.
Well 9T | Ekulama 2 | 15 | 1994 | 17 | Replace by 2018 | 2009 | Flowline Expired
Well 39L | Ekulama 2 | 15 | 2019 | 2 | Replace 2034 | 2033 |  |  | Replaced in 2019.
Well 39S | Ekulama 2 | 15 | 1991 | 29 |  | 2006 | Flowline Expired | 1. Complete replacement. 2. Carry out UT to determine what integrity index is remaining. | No clamp
Well 22L | Ekulama 2 | 15 | 2017 | 3 | Replace by 2030 | 2032 |  | 1. Fix all Cathodic Protection issues. 2. Repair field joint wrapping. 3. Carry out 3 yearly UT (in plot/on plot piping) inspection of our flow lines and manifold piping's. 4. Increase ROW Surveillance. | No clamp
Well 24T | Ekulama 2 | 15 | 2010 | 10 | Replace by 2022 | 2025 |  |  | Flow line clamped once

## Awoba Flowline Integrity status
flowline | location | design_life_span | year_Installed_or_replaced | years_installed_or_laid | planned_replacement_period | latest_replacement_date | complete_system_failure_indicator | preventive_maintenace_plan | remarks
Well 2T | awoba | 15 | 2012 | 8 | Replace 2024 | 2027 |  | 1. Carry out 3 yearly UT (in plot/on plot piping) inspection of our flow lines and manifold piping's. 2. Increase ROW Surveillance.
Well 3L | awoba | 15 | 2011 | 9 | Replace 2023 | 2026 |  | 1. Carry out 3 yearly UT (in plot/on plot piping) inspection of our flow lines and manifold piping's. 2. Increase ROW Surveillance. | O/U 31/10/2015
Well 3S | awoba | 15 | 2011 | 9 | Replace by 2023 | 2026 |  | 1. Carry out 3 yearly UT (in plot/on plot piping) inspection of our flow lines and manifold piping's. 2. Increase ROW Surveillance. | O/U 31/10/2016
Well 6L | awoba | 15 | 1991/2016 | 5 | Replace by 2029 | 2031 |  | None OK | First line was laid in 1991 and replaced 2016
Well 7L | awoba | 15 | 1990 | 30 | Replace Now | 2005 | Flowline Expired | 1. Complete replacement Now. 2. Increase ROW Surveillance | 4 nos Clamps at different sections already done
Well 7S | awoba | 15 | 2009 | 11 | Replace by 2021 | 2024 | Flowline at Risk | 1. Complete replacement Now. 2. Increase ROW Surveillance | 7 nos of Clamps at different sections already carried out.Shelf life not expired but susceptible
Well 8T | awoba | 15 | 2011 | 9 | Replace by 2026 | 2026 |  | 1. Carry out 3 yearly UT (in plot/on plot piping) inspection of our flow lines and manifold piping's. 2. Increase ROW Surveillance.
Well 9S | awoba | 15 | 1991/2016 | 5 | Replace by 2029 | 2031 |  | 1. Carry out 3 yearly UT (in plot/on plot piping) inspection of our flow lines and manifold piping's. 2. Increase ROW Surveillance. | Flowline was replaced in 2016
6" delivery Line (old) | awoba | [5 empty] | Flowline at Risk | 1. Carry out integrity test to determine line condition 2. Replace line based on test result. 3. Increase ROW Surveillance | Clampping @ ROW in 2017 and 2020
6" delivery Line (new) | awoba | [5 empty] | Flowline at Risk | 1. Carry out integrity test to determine line condition 2. Replace line based on test result. 3. Increase ROW Surveillance | Awaiting mangement Approval to fix leaks on pipeline.